## Hoja1
CONSTANT TASKS NOT INCLUDED IN THE LIST |  | CONSTANT TASKS NOT INCLUDED IN REQUIREMENTS LIST
SYSTEMS | User support for all external translators and users of Transtation and Dubstation. Installing issues. Windows OS firewall and antivirus reconfiguration for externaul users. Scripts manually parsing and error finding. Video troubleshooting. Real time support with remote desktop if needed. In-office user support for Dubstation, Prepstation and QCstation.
NETWORK | Email cleaning, Aspera Connect accounts creation, Archiware Prestore mounting and maintenance of server fiber card drivers, P5 tool review, tapes review. Dongle security keys programing. Firewall security. Aspera monitoring. Linux servers maintenance.
REQUIREMENTS LIST
AREA | TYPE | DESCRIPTION | PRIORITY | START DATE | STATUS | END DATE | VERSION
DEVELOPMENT:Transtation | Exporting | STL Subtitles File Exporting separated by font style and position to use in Avid Media Composer burning. |  | 2013-01-05 | COMPLETED | 07/15/2013 | 3_4_709
DEVELOPMENT:Transtation | Functionality | Higher resolution video player with support of H264 .mov format for accurate lyp-sync. |  | 2013-01-05 | COMPLETED | 2013-01-09 | 3_4_718
DEVELOPMENT:Dubstation | Functionality | Higher resolution video player with support of H264 .mov format for accurate lyp-sync. |  | 2013-01-05 | COMPLETED | 2013-12-10 | 2_9_28
DEVELOPMENT:Transtation | Exporting | SRT Subtitles File Importing and Exporting to use with Asian/Arabic languages |  | 2013-01-05 | COMPLETED | 01/27/2014 | 3_4_719
DEVELOPMENT:Dubstation | Functionality | Generation of SMTPE Time Code signal using Adrienne TC Card in synchronization with Dubstation video playing and comunication of signal to Midi Timepiece to control MAC Protools Digital Audio system to complete dubbing and recording chain. |  | 2013-01-05 | COMPLETED | 02/13/2014 | 2_9_29
DEVELOPMENT:Dubstation | Functionality | Reading of Drop Frame and Non Drop Frame information from video metadata prepared with PREPstation. |  | 2013-01-05 | COMPLETED | 01/15/2014 | 2_9_27
DEVELOPMENT:Prepstation | Functionality | Inclusion of options for video prepping: Frame Rate (24F,PAL,NTSC), Frame Dropping(DF, NDF) and Use For(Dubbing, Subtitling). All info is saved as part of video metadata to be read by Dubstation. |  | 2013-01-05 | COMPLETED | 01/15/2014 | 1_7
DEVELOPMENT:Transtation | Functionality | Transtation support of .mov files with different frame rates (PAL,NTSC) |  | 2014-09-03 | COMPLETED | 2014-11-03 | 3_4_721
DEVELOPMENT:Transtation | Functionality | Inclusion of menu option to deactivate OFF camera flag for dialogs creation. |  | 2014-12-03 | COMPLETED | 03/14/2014 | 3_4_722
DEVELOPMENT:Dubstation | Functionality | CINEMA 24F Videos support for Dubstation with Adrienne TC Card and Protools locking at 24F. |  | 2014-04-04 | COMPLETED | 04/15/2014 | 2_9_31
DEVELOPMENT:Transtation | Functionality | CINEMA 24F Videos support in Transtation. |  | 04/18/2014 | COMPLETED | 04/22/2014 | 3_4_723
DEVELOPMENT:Transtation | Security | User security control and email sending to enginnering department with user account information: IP address and computer full name. |  | 04/30/2014 | COMPLETED | 2014-05-05 | 3_4_723
DEVELOPMENT:Dubstation | Security | User security control and email sending to enginnering department with user account information: IP address and computer full name. |  | 04/30/2014 | COMPLETED | 2014-09-06 | 2_9_32
DEVELOPMENT:QCStation | Security | User security control and email sending to enginnering department with user account information: IP address and computer full name. |  | 04/30/2014 | COMPLETED | 2014-05-07 | 1_3_1
ADMINISTRATION:Network | Servers | Standarization of Terrablock Mounting procedure (Active Directory, users scripts). |  | 2014-05-06 | COMPLETED | 07/20/2014
ADMINISTRATION:Network | Upgrade | Terrablock servers updgrade and mounting scripts. |  | 08/13/2014 | COMPLETED | 08/13/2014
ADMINISTRATION:Network | Security | BBCW Third party Network Security Compliance Requirements review and question answering. Data and media protection policy creation. Information security policy creation. |  | 08/18/2014 | COMPLETED | 08/22/2014
ADMINISTRATION:Network | Security | Security Advisory: Aspera Upgrade |  | 09/26/2014 | COMPLETED | 2014-07-10
DEVELOPMENT:Prepstation | Functionality | Prepstation Video Encryption. |  | 08/18/2014 | COMPLETED | 2015-04-03 | 1_8
DEVELOPMENT:Transtation | Functionality | Transtation Video Encrypted Player. |  | 08/18/2014 | COMPLETED | 03/31/2015 | 3_5_1
ADMINISTRATION:Network | Security | BBC, I reviewed the Content Security Compliance document and identify specific requirements where network and equipment improvements are needed. New anser document:Security Compliance Checklist Content Protection V1 Kitchen Infosec Comments 03-12-14 Rev1 |  | 2014-11-11 | COMPLETED | 2014-03-12
DEVELOPMENT:Transtation | Functionality | MP4 Video Player |  | 12/31/2014 | COMPLETED | 03/31/2015 | 3_5_1
ADMINISTRATION:Network | Security | ASPERA serever FASPEX SSL certificate installing. |  | 01/19/2015 | COMPLETED | 01/19/2015
DEVELOPMENT:Transtation | Functionality | STL exporting of special characters for Scandinavian languages. Example: Å, ø, å, so they can burn them in Media Composer. |  | 01/29/2015 | COMPLETED | 2015-02-02 | 3_4_724
ADMINISTRATION:Network | Security | BBC Network Requirements revision: Risk Assessment, Intrusion detection system (IDS), Network Penetration Testing. Intrusion detection activated 03/17. Light pentest with NMAP. |  | 02/17/2015 | WAITING | 03/23/2015
DEVELOPMENT:Transtation | Importing | Softni subtitles SUB file importing: portuguese special characters recognition and subtitles position, so now they can be burned in Media Composer with correct positions and accents. |  | 02/16/2015 | COMPLETED | 02/23/2015 | 3_4_725
DEVELOPMENT:Transtation | Importing | SRT importing for files from "Gustavo H M Silva, Synapse Produções, Brasil" to solve their problem with italics marking. |  | 02/23/2015 | COMPLETED | 02/25/2015 | 3_4_726
ADMINISTRATION:Network | Servers | AVG Antivirus error message, license syncronization in all network computers. |  | 02/23/2015 | COMPLETED | 2015-09-03 | 1_8
DEVELOPMENT:QCstation | Issue | Issue opening MP3 audio files. Library fixing. New version installed. |  | 2015-04-03 |  | 2015-04-03 | 1_3_1
DEVELOPMENT:QCstation | Porting | Testing and porting of QCstation to Windows 7. |  | 2015-06-03 |  | 2015-08-04 | 1_3_2
DEVELOPMENT:Dubstation | Porting | Testing and porting of Dubstation to Windows 7. |  | 2015-06-03 | COMPLETED | 2015-01-06 | 2_9_37
DEVELOPMENT:Transtation | Exporting | Export to AVID DS subtitles file format, to support Asian lenguages in Media Composer allowing subtitles burning in the HUB. | 2 | 03/18/2015 | COMPLETED | 05/29/2015 | 3_4_730
ADMINISTRATION:Network | Install | Install new version of Prepstation in Edit03 as part of recording department growing. |  | 03/23/2015 | COMPLETED | 03/24/2015
ADMINISTRATION:Network | Servers | Mount DocServer in Prestore server to do daily backups. |  | 03/31/2015 | COMPLETED | 2015-01-04
ADMINISTRATION:Network | Internet | Watchguard Firewall configuration problem: two Ips activated for outgoing traffic: 68.67.211.231, 68.67.211.254. Reconfiguration to use only: 68.67.211.254. |  | 2015-02-04 | COMPLETED | 2015-06-04
DEVELOPMENT:Transtation | Exporting | STL subtitles file extra lines and spaces recognition and erasing, position recognition, italics recognition. |  | 2015-03-04 | COMPLETED | 2015-06-04 | 3_4_728(installed)
DEVELOPMENT:Dubstation | Functionality | Current script saving when user open a new script or close Dubstation. Allow only one instance of Dubstation running. Force use of scripts local folder to open scripts. | 1 | 04/21/2015 | COMPLETED | 05/22/2015 | 2_9_37(installed)
DEVELOPMENT:Transtation | Functionality | Document generation with side by side original and translated script comparision for translation quality control. Automatic detection of deleted or inserted dialogs in traslated script, time code changes, automatic dialog merging and marking. |  | 04/27/2015 | COMPLETED | 2015-07-05 | 3_4_729
ADMINISTRATION:Network | Servers | Aspera server point to point connection revision for Deluxe client. |  | 2015-07-05 | COMPLETED | 2015-07-05
ADMINISTRATION:Network | Servers | Prestore server upgrade. P5 tool upgrade to V.5.1.9. Tape issue identification and solution. |  | 04/29/2015 | COMPLETED | 05/26/2015
ADMINISTRATION:Network | Servers | Aspera faspex file upload issue, client Globalcast. Server review. Findings: client error sending package to wrong address. |  | 05/15/2015 | COMPLETED | 05/15/2015
ADMINISTRATION:Network | Servers | Aspera faspex services corrupted. Asperea user support contacted and conference to solve problem. Problem solved rebooting aspera faspex services. |  | 05/19/2015 | COMPLETED | 05/19/2015
DEVELOPMENT:Transtation | Issue | Audio/Video unsync problem with some videos | ADDED | 05/16/2015 | COMPLETED | 05/22/2015 | 3_5_2
ADMINISTRATION:Dubstation | Installing | Install last version in all Windows XP record computers. | 3 | 05/22/2015 | COMPLETED | 05/22/2015 | 2_9_37
ADMINISTRATION:Dubstation | Testing | Review last version in Windows 7 record computers. | 4 | 2015-01-06 | COMPLETED | 2015-01-06 | 2_9_37
ADMINISTRATION:Network | Servers | FTP bandwith and banning review with Crushadmin Tool | ADDED | 05/31/2015 | COMPLETED | 2015-03-06
DEVELOPMENT:Prepstation | Functionality | Question Adrienne 23.98 framerate TC generation. Email sent to Adrienne support, incomplete answer from them. Researching to send new email. | ADDED | 2015-05-06 | WORKING
DEVELOPMENT:Transtation | Exporting | Review SUB exporting position marks {{{{{ | 7 | 2015-01-06 | WORKING
DEVELOPMENT:Prepstation | Functionality | Video recompress with no encryption for new player. | 8 | 2015-01-06 | WORKING
ADMINISTRATION:QCStation | Installing | Install last version in all production computers. | 5 | 2015-01-06 | WORKING
ADMINISTRATION:Transtation | Installing | Install last version in language department computers | 6 | 2015-01-06 | WORKING
ADMINISTRATION:Network | Issue | Email/Internet/Word slow issue. WatchGuard Firewall review. | ADDED | 2015-04-06 | WORKING
ADMINISTRATION:Transtation | Installing | Install encrypted version in Laura computer to do more testing | 9
DEVELOPMENT:Transtation | Issue | Interleave - The number entered should be the same as the frame difference stamped. | 10
DEVELOPMENT:Transtation | Issue | Reading speed error note for dark REDs and dark BLUEs only. | 11
DEVELOPMENT:Transtation | Issue | Blues too long on-air will turn white. They should keep the blue. | 12
DEVELOPMENT:Transtation | Issue | Subs in blues are not popping any error note with CTRL+K. | 13
DEVELOPMENT:Transtation | Issue | To prompt an window with exact time code whenever is an error in the time code bar. Not to do line count until error is revised. | 14
ADMINISTRATION:Network | Security | Complete intrusion detection testing and security controls for users internet access (WatchGuard Firewall Configuration). | 15
ADMINISTRATION:Network | Users | Windows XP to Windows 7 upgrade. User privileges, Terrablock and Engineering on Windows 7. | 16
DEVELOPMENT:Transtation | Exporting | Review of SAMI exporting. | 17
DEVELOPMENT:Transtation | Functionality | Subtitles over video simulation. | 18
DEVELOPMENT:Transtation | Tools | Side by side document to compare original and translated language SUB scripts. | 19
DEVELOPMENT:Transtation | Tools | Separate SUB (archive) from DUB in a hybrid document. | 20
ADMINISTRATION:Network | Users | Include Mac's in Active Directory, or have Mac server with separate administration | 21
DEVELOPMENT:Transtation | Exporting | PAC format. | 22
DEVELOPMENT:Transtation | Exporting | SCC format and DXFP (close caption) format. | 23